PHOTOGRAPHY SHOOT GUIDELINES.

FOR THE NHSScotland Photo Library

www.nhsscotlandphotolibrary.org

Arranging a photo shoot in a clinical or working setting - points to note.

These should help you avoid some of the pitfalls that arise with photography in a busy working environment.

Decide what scenarios you want to capture. Estimate the time involved - this is not straightforward. Photographing a single straightforward consultation will typically take 15-20 minutes but longer will be required if there are many subjects or a variety of compositions, poses, rooms or equipment. 12-15 scenarios in one location are likely to take most of a day. This might yield 100 different images.

List the likely participants or models required(nurse, doctor, child, physio) and the type of location(hospital, health centre, street, home, studio).

Make contact with the communications team or management team responsible for the location you wish to visit. Explain the nature and value of the NHSScotland photo library  www.nhsscotlandphotolibrary.org  and the type of shots you are hoping to capture on the day. Send copies of the consent form and question and answer sheets for information. These documents are all found under Photographer Guidelines on the site.

Offer to visit the location at a time that will suit all those needed. Ensure that all managers are happy for the photographer to visit. Request that a well known local member of staff can be available, or at least contactable, for introductions and assistance throughout the day as this will facilitate matters. If you can visit ahead of the shoot take notice of the space available and any hazards or problems that might hamper the photographer.

Offer to supply copies of the consent forms ahead of time but beware  - you may then get some forms for individuals who will not be present on the day and other forms where you do not know which form applies to which person. If this is the case, take copies of the completed forms on the day and note a description of each subject photographed on the relevant form. All participants - including staff - must complete a consent form. A home address is preferred.  If a work address is given, it should include full postal address and post code.

Confirm the date and time of the photo shoot with the team/participants/facility manager.  Contact your photographer with details of the time and location, parking arrangements, meeting point and local contact name and number.  Make sure they have signed a copy of the contract, waiving copyright to the Crown / NHSScotland and know the technical requirements for the images document in the Photographers Guidelines section on the website www.nhsscotlandphotolibrary.org   Please ask them to make a point of taking a basic head and shoulders shot of all participants wherever possible.

On the day, arrive in good time. Take a clipboard with blank consent forms (www.nhsscotlandphotolibrary.org)   interleaved with Information Sheets www.nhsscotlandphotolibrary.org  which will answer most questions that models have, and make sure the forms are completed by any participants.

Introduce your photographer to the site contact. Reiterate what you are hoping to achieve and ask what problems they foresee - and what other opportunities there might be to fit in to the schedule if the photographer is willing.

Find out if you can leave coats and bags in a secure place. Travel light and wear comfortable shoes.

Take note of the surroundings - are they clean and tidy, is equipment correctly stored or positioned? Politely prompt staff to check that the appearances are as they should be - and that everyone is observing relevant dress code or uniform guidelines.

If procedures or treatments are taking place make sure the photographer understands what is to happen in what order - ask the health care professional to talk through what they will do.  Watch the photographer at work and direct as necessary - be clear about what equipment or props are to be used and try and ensure that a good variety of shots  for each set up is taken (eg landscape, portrait, close up and wide). Shots that preserve anonymity will always be useful in addition to those that show faces clearly.

Thank all participants at the end of each set of shots. The vast majority of staff and patients approached to date have been happy to take part. Be aware of subject's state of health and check that they are happy during and at the end of photography. Reiterate that they can change their minds during the photo shoot or ask the photographer to stop at any point.

In a busy working environment this will be a lot to manage. Keeping the paperwork organised and description completed will be the key factor in listing and categorising the images later.

As soon as possible after the shoot, match up the images with the consent forms and note any extra information you have captured. Scan the consent forms to create electronic copies and save each file as surname_firstname.pdf. Save the head and shoulders shots as surname_firstname.jpg at medium quality and approx 300 pixels width. Complete a captioning excel file sheet  following the example on the site provided very closely.  Consent forms need to be securely stored under the terms of the Data Protection Act.